## ورقة1
EXPECTED TIME (ET) | TIME ESTIMATE
o + 4r + p | (in days) |  |  | ACTIVITY
6 | p | r | o
7.8333 | 10 | 8 | 5 |  | 1. Requirements collection
3 | 5 | 3 | 1 |  | 2. Report Design
4 | 6 | 4 | 2 |  | 3. Screen Design
6 | 9 | 6 | 3 |  | 4. Database Design
4.3333 | 7 | 4 | 3 |  | 5. User Documentation
7 | 9 | 7 | 5 |  | 6. Programming
3 | 5 | 3 | 1 |  | 7. Testing
4 | 6 | 4 | 2 |  | 8. Installation
39.1667